## RTM
Requirement Traceability Matrix — Student Attendance System
Req. ID | Requirement Description | Type | Source / Use Case | Design Ref. | Test Case ID(s) | Status
FR-01 | The system shall allow faculty to mark attendance for an entire class session. | Functional (Must) | UC-01 | App Layer - Attendance Capture Service | TC-01 | Proposed / Not yet implemented
FR-02 | The system shall support RFID/biometric-based check-in for students. | Functional (Must) | UC-01 | App Layer - Attendance Capture Service | TC-02 | Proposed / Not yet implemented
FR-03 | The system shall allow students to self-check-in via a session QR code. | Functional (Should) | UC-01 | App Layer - Attendance Capture Service | TC-03 | Proposed / Not yet implemented
FR-04 | The system shall timestamp every attendance entry with session, subject, and date. | Functional (Must) | UC-01 | App Layer - Attendance Capture Service | TC-04 | Proposed / Not yet implemented
FR-05 | The system shall allow students to submit leave requests with reason and optional supporting document. | Functional (Should) | UC-03 | App Layer - Leave Management Service | TC-05, TC-06 | Proposed / Not yet implemented
FR-06 | The system shall allow faculty to approve or reject pending leave requests. | Functional (Should) | UC-04 | App Layer - Leave Management Service | TC-07, TC-08 | Proposed / Not yet implemented
FR-07 | Approved leave shall automatically factor into attendance-percentage calculations. | Functional (Should) | UC-03, UC-04 | App Layer - Leave Management Service | TC-09 | Proposed / Not yet implemented
FR-08 | The system shall generate attendance reports filtered by student, course, or date range. | Functional (Must) | UC-05 | App Layer - Reporting & Analytics Module | TC-10 | Proposed / Not yet implemented
FR-09 | The system shall export attendance reports to PDF and Excel formats. | Functional (Should) | UC-12 | App Layer - Reporting & Analytics Module | TC-11 | Proposed / Not yet implemented
FR-10 | The system shall display a class-wise attendance analytics dashboard for faculty and HOD. | Functional (Should) | UC-06 | App Layer - Reporting & Analytics Module | TC-12 | Proposed / Not yet implemented
FR-11 | The system shall automatically send an SMS/email alert when a student's attendance drops below 75%. | Functional (Must) | UC-07 | App Layer - Notification & Alert Engine | TC-13, TC-14 | Proposed / Not yet implemented
FR-12 | The system shall notify a parent/guardian of a child's daily absence. | Functional (Should) | UC-07 | App Layer - Notification & Alert Engine | TC-15 | Proposed / Not yet implemented
FR-13 | The administrator shall be able to manage user accounts and role assignments. | Functional (Must) | UC-09 | App Layer - Auth & User Mgmt | TC-16 | Proposed / Not yet implemented
FR-14 | The administrator shall be able to configure courses, timetables, and attendance rules. | Functional (Must) | UC-08, UC-10 | App Layer - Auth & User Mgmt | TC-17 | Proposed / Not yet implemented
FR-15 | The system shall maintain an audit log of all attendance edits with user ID and timestamp. | Functional (Should) | UC-11 | App Layer - Auth & User Mgmt | TC-18 | Proposed / Not yet implemented
FR-16 | The system shall synchronize enrollment and timetable data with the institution's ERP/LMS. | Functional (Must) | System-wide | Cross-cutting (all layers) | TC-19 | Proposed / Not yet implemented
NFR-01 | Attendance capture (RFID/biometric scan) shall complete within 2 seconds per student. | Non-Functional - Performance (Must) | System-wide | Cross-cutting (all layers) | TC-20 | Proposed / Not yet implemented
NFR-02 | The system shall support 10,000+ concurrent students during peak class-change hours (8-9 AM). | Non-Functional - Scalability (Should) | System-wide | Cross-cutting (all layers) | - | Proposed / Not yet implemented
NFR-03 | The system shall maintain 99.5% uptime during institutional working hours. | Non-Functional - Availability (Must) | System-wide | Cross-cutting (all layers) | - | Proposed / Not yet implemented
NFR-04 | The mobile app shall cache attendance offline and auto-sync on reconnect, with zero data loss. | Non-Functional - Reliability (Should) | System-wide | Cross-cutting (all layers) | - | Proposed / Not yet implemented
NFR-05 | The system shall enforce role-based access control (RBAC) and encrypt biometric templates at rest and in transit. | Non-Functional - Security (Must) | System-wide | Cross-cutting (all layers) | - | Proposed / Not yet implemented
NFR-06 | The system shall comply with India's DPDP Act, 2023 for storage/processing of biometric and personal data. | Non-Functional - Compliance (Must) | System-wide | Cross-cutting (all layers) | - | Proposed / Not yet implemented
NFR-07 | Faculty shall be able to complete a full class attendance session in no more than 3 taps/clicks per student. | Non-Functional - Usability (Should) | System-wide | Cross-cutting (all layers) | - | Proposed / Not yet implemented
NFR-08 | The system shall use a modular architecture allowing new capture modes to be added without disrupting existing modules. | Non-Functional - Maintainability (Should) | System-wide | Cross-cutting (all layers) | - | Proposed / Not yet implemented
NFR-09 | The system shall expose REST APIs for integration with the institution's ERP/LMS. | Non-Functional - Interoperability (Should) | System-wide | Cross-cutting (all layers) | - | Proposed / Not yet implemented
NFR-10 | The mobile application shall run on Android 10+ and iOS 14+. | Non-Functional - Portability (Could) | System-wide | Cross-cutting (all layers) | - | Proposed / Not yet implemented

## WBS
Work Breakdown Structure — Student Attendance System
WBS ID | Task | Deliverable | Duration (days)
1.0 | Project Initiation | Charter, scope statement | 3
1.1 | Define problem statement & objectives | Problem Statement | 1
1.2 | Identify stakeholders | Stakeholder Matrix | 1
1.3 | Feasibility study (TELOS) | Feasibility note | 1
2.0 | Requirements Engineering | SRS document | 8
2.1 | Elicit requirements (interviews, surveys, observation) | Raw requirement notes | 2
2.2 | Analyse & prioritise (MoSCoW) | Prioritised FR/NFR list | 2
2.3 | Write SRS (IEEE 830) | SRS_Student_Attendance_System.docx | 3
2.4 | Review & validate SRS | Reviewed & baselined SRS | 1
3.0 | System Design | Design documents | 6
3.1 | Draw context diagram & DFD | Context Diagram | 1
3.2 | Draw UML use case diagram | Use Case Diagram | 1
3.3 | Design system architecture | Architecture Diagram | 2
3.4 | Design database schema | ER diagram / schema | 2
4.0 | Implementation | Working modules | 12
4.1 | Develop Auth & User module | Login/Registration module | 3
4.2 | Develop Attendance Capture module (RFID/biometric/QR) | Attendance capture module | 4
4.3 | Develop Leave Management module | Leave workflow module | 3
4.4 | Develop Notification & Reporting module | Alert & report engine | 2
5.0 | Testing | Test artifacts | 5
5.1 | Prepare test cases | Test Case sheet | 2
5.2 | Execute functional testing | Executed test log | 2
5.3 | Log & triage bugs | Bug report sheet | 1
6.0 | Deployment & Documentation | Final submission | 3
6.1 | Prepare GitHub repository & README | GitHub README | 1
6.2 | Prepare presentation & viva notes | Presentation deck | 1
6.3 | Final review & submission | Complete Practical 2 package | 1

## Gantt Chart
Gantt Chart — Student Attendance System (Duration in Days)
WBS ID | Task | D1 | D2 | D3 | D4 | D5 | D6 | D7 | D8 | D9 | D10 | D11 | D12 | D13 | D14 | D15 | D16 | D17 | D18 | D19 | D20 | D21 | D22 | D23 | D24 | D25 | D26 | D27 | D28 | D29 | D30 | D31 | D32 | D33 | D34 | D35 | D36 | D37
1.0 | Project Initiation
2.0 | Requirements Engineering
3.0 | System Design
4.0 | Implementation
5.0 | Testing
6.0 | Deployment & Documentation
Note: D1-D37 represent project working days from project start (college-project scale, ~5.3 weeks). Bars are illustrative planning estimates.

## Agile Backlog
Product Backlog — Student Attendance System
Backlog ID | Epic | User Story | Priority (MoSCoW) | Story Points | Acceptance Criteria (Given-When-Then)
PB-01 | User Access | As a student, I want to register with my student ID, so that I can access the attendance portal. | Must | 3 | Given a valid student ID, When I submit the registration form, Then my account is created and I can log in.
PB-02 | User Access | As a user, I want to log in securely, so that I can view my own attendance. | Must | 2 | Given valid credentials, When I submit the login form, Then I am taken to my dashboard.
PB-03 | Attendance Capture | As a faculty member, I want to mark attendance via RFID/biometric, so that recording is fast and accurate. | Must | 5 | Given an active session, When I scan a student's RFID/biometric, Then their attendance is recorded with a timestamp.
PB-04 | Attendance Capture | As a student, I want to self-check-in via a QR code, so that attendance is captured even if faculty is occupied. | Should | 3 | Given a valid session QR code, When I scan it within the session window, Then my attendance is marked present.
PB-05 | Leave Management | As a student, I want to apply for leave online, so that I don't need a physical form. | Must | 3 | Given a reason and optional document, When I submit a leave request, Then it appears in my faculty's approval queue.
PB-06 | Leave Management | As a faculty member, I want to approve or reject leave requests, so that attendance records stay accurate. | Must | 3 | Given a pending leave request, When I approve or reject it, Then the student's attendance record updates accordingly.
PB-07 | Notifications | As a parent, I want to receive an alert when my child is absent, so that I am informed the same day. | Should | 3 | Given a student is marked absent, When the day's session ends, Then a notification is sent to the registered parent contact.
PB-08 | Notifications | As a student, I want an alert when my attendance drops below 75%, so that I can take corrective action. | Must | 5 | Given a student's attendance falls below 75%, When the nightly calculation runs, Then an SMS/email alert is sent to the student and parent.
PB-09 | Reporting | As a faculty member, I want a class-wise attendance dashboard, so that I can spot trends quickly. | Should | 5 | Given a selected course, When I open the analytics dashboard, Then attendance trends are shown visually.
PB-10 | Reporting | As an administrator, I want to export attendance reports to PDF/Excel, so that I can share them with management. | Should | 3 | Given a generated report, When I click export, Then a PDF or Excel file is downloaded with the report data.
PB-11 | Admin | As an administrator, I want to manage user accounts and timetables, so that the system reflects the current semester. | Must | 5 | Given valid details, When I add/edit/deactivate a user or timetable entry, Then the change reflects across the system.
PB-12 | Non-functional | As a product owner, I want attendance capture to respond within 2 seconds, so that class time is not wasted. | Should | 3 | Given a normal-load session, When a student checks in, Then the confirmation is shown within 2 seconds.
Sprint Plan (2-week sprints, illustrative)
Sprint | Stories Included | Sprint Goal
Sprint 1 | PB-01, PB-02, PB-11 | Set up member auth and admin user/timetable management
Sprint 2 | PB-03, PB-04, PB-05 | Deliver core attendance capture and leave request submission
Sprint 3 | PB-06, PB-07, PB-08 | Add leave approval workflow and attendance alerts
Sprint 4 | PB-09, PB-10, PB-12 | Add reporting dashboards, exports, and performance tuning

## Test Cases
Sample / Proposed Test Cases — Student Attendance System
Test Case ID | Requirement(s) | Use Case | Test Description | Test Steps | Expected Result
TC-01 | FR-01 | UC-01 | Verify faculty can mark attendance for a full class session | Faculty opens session, selects all present students, and submits | Attendance is recorded for the session with correct timestamp
TC-02 | FR-02 | UC-01 | Verify RFID/biometric-based student check-in | Student taps RFID card / scans biometric at classroom reader | Attendance is marked present within 2 seconds
TC-03 | FR-03 | UC-01 | Verify QR code self-check-in | Student scans the session QR code displayed by faculty | Attendance is marked present for that session
TC-04 | FR-04 | UC-01 | Verify attendance entry is timestamped correctly | Mark attendance for a student and inspect the stored record | Record includes correct session, subject, and date/time
TC-05 | FR-05 | UC-03 | Verify leave request submission | Student enters reason and submits a leave request | Leave request appears in faculty's pending-approval queue
TC-06 | FR-05 | UC-03 | Verify leave request with supporting document | Student attaches a document while submitting a leave request | Document is stored and visible to faculty during review
TC-07 | FR-06 | UC-04 | Verify faculty can approve a leave request | Faculty opens a pending leave request and clicks Approve | Request status changes to Approved and student is notified
TC-08 | FR-06 | UC-04 | Verify faculty can reject a leave request | Faculty opens a pending leave request and clicks Reject | Request status changes to Rejected and student is notified
TC-09 | FR-07 | UC-03, UC-04 | Verify approved leave adjusts attendance percentage | Approve a leave request for a session already marked absent | Attendance percentage recalculates to exclude the approved-leave session
TC-10 | FR-08 | UC-05 | Verify attendance report generation by date range | Faculty selects a course and date range, clicks Generate Report | Report displays attendance data filtered to the selected range
TC-11 | FR-09 | UC-12 | Verify report export to PDF/Excel | Generate a report and click Export, choosing PDF or Excel | A correctly formatted file downloads with matching report data
TC-12 | FR-10 | UC-06 | Verify class-wise analytics dashboard | Faculty opens the analytics dashboard for a selected class | Attendance trend charts render with accurate underlying data
TC-13 | FR-11 | UC-07 | Verify low-attendance alert is triggered below 75% | Simulate a student's attendance dropping to 74% | SMS/email alert is sent to the student and parent
TC-14 | FR-11 | UC-07 | Verify alert is not sent when attendance is at or above 75% | Simulate a student's attendance at exactly 75% | No low-attendance alert is sent
TC-15 | FR-12 | UC-07 | Verify parent notification of daily absence | Mark a student absent for the day's sessions | Registered parent contact receives an absence notification
TC-16 | FR-13 | UC-09 | Verify admin can create and deactivate a user account | Admin creates a new student account, then deactivates it | Account is created, then login is blocked after deactivation
TC-17 | FR-14 | UC-08, UC-10 | Verify admin can configure timetable and attendance-rule threshold | Admin updates a course timetable and changes the alert threshold | New timetable and threshold values are saved and applied
TC-18 | FR-15 | UC-11 | Verify audit log records an attendance edit | Faculty edits a previously marked attendance entry | Audit log records the change with user ID and timestamp
TC-19 | FR-16 | System-wide | Verify ERP/LMS enrollment sync | Trigger a sync job with the institution's ERP/LMS | Enrollment and timetable data update to match the ERP/LMS source
TC-20 | NFR-01 | UC-01 | Verify attendance capture response time | Perform an RFID/biometric check-in under normal system load | Confirmation is returned within 2 seconds
Note: These are proposed/sample test cases for planning purposes; no claim is made that testing has actually been executed.

## Sample Bug Reports
Sample / Proposed Bug Reports — Student Attendance System
Bug ID | Related Test Case | Severity | Description | Likely Root Cause | Status | Suggested Fix
BUG-01 | TC-14 | Medium | Low-attendance alert incorrectly triggered for a student at exactly 75.00% due to floating-point comparison | Boundary condition where 75.00% was treated as < 75 due to float rounding | Open | Use fixed-point/decimal comparison for attendance-percentage threshold checks
BUG-02 | TC-03 | Low | QR self-check-in occasionally accepted after the session window has closed | Missing server-side validation of session end-time before accepting scan | Open | Add server-side timestamp validation against the active session window
BUG-03 | TC-09 | High | Attendance percentage double-counts a session as both 'absent' and 'approved leave' when leave is approved after marking | Leave approval and daily attendance aggregation are not mutually exclusive in the calculation query | Open | Add a mutual-exclusion check so approved leave overrides a prior absent mark
BUG-04 | TC-13 | Medium | Low-attendance SMS occasionally sent twice for the same student on the same day | Notification scheduler job overlaps when the server restarts mid-cycle | Open | Add a duplicate-send guard keyed by student ID and notification date
BUG-05 | TC-02 | Low | RFID reader occasionally registers two attendance entries for one tap due to signal bounce | No debounce window on the RFID reader input handler | Open | Add a short debounce window (e.g., 5 seconds) per student per session
Note: These are sample/hypothetical bug reports proposed for illustration; no actual testing was performed and no real bugs were found.

## Software Engineering Tools
Software Engineering Tools Used — Student Attendance System
Tool | Purpose in this Assignment | Artifact Produced
Microsoft Word | Writing the IEEE 830-style SRS document | SRS_Student_Attendance_System.docx
Microsoft Excel | Building the RTM, WBS, Gantt chart, Agile backlog, and testing artifacts | SAS_Artifacts.xlsx
Draw.io / diagrams.net (or equivalent diagramming) | Creating the Context Diagram, UML Use Case Diagram, and Stakeholder Matrix | SAS_Context_Diagram.png, SAS_Use_Case_Diagram.png, diagrams embedded in SRS
GitHub | Version control and hosting of source code, with commit history as evidence of iterative development | SAS_GitHub_README.md and repository